Task 1

  - Evaluate the procurement method for this project and identify the contract document.

The building owner needs an early start of the project and wishes have the knowledge and experience of the contract at the design stage. So Here according to my observation I think more suitable procurement method for this project was based on bills of firm quantities By selecting firm quantities method, we can achieve following advantages.

- Both parties have a clear picture of the extent of their respective commitments

- The unit rates in the bills provide a sound basis for the valuate of any variations to the design

- A detailed breakdown of the tender sum is readily available

The essential characteristics of this method are

- that both the quantities and the unit rates in the bill form part of the contract and

- That virtual completion of the design precedes the signing of the contract. Such a contract is a lump sum contract (sometimes called a fixed price contract) because a price is stated in the contract as payment for the work described in the bill.

The contract document for above project comprises:

- Form of contract

- Bills of Quantity

- Specification

- Drawings

  - Assess the usefulness of the above contract document for proper execution of the contract

The Contract Documents

The contract document comprises the entire agreement between Client and the contractor concerning the work. The contract documents will be censured in accordance with the legislation. Also it is describing functional completion of a project.

The number and nature of the contract documents will normally associated with those of the tender documents. According to the given project, JCT 98 Private Edition with Quantities has been used as the conditions of contract and the following contract documents are likely to be received by the contractor.

Form of contract

This is the principal document and will often be a printed standard form, such as one of the variants of the JCT Form. This consists of three parts:

- The articles of agreement, which is the actual contract which the parties sign,

- The Conditions (subdivided into five sections), which set out the obligations and rights of the Parties and detail the conditions under which the contract is to be carried out.

- Supplemental provision which sets out the rights and liabilities of the parties in regard to  Value added tax (VAT)

The Articles of Agreement

- It is sometimes necessary for the printed text of a clause of a standard form to be amended, added to or deleted in order to accommodate particular requirements of a building owner or because the standard wording does not suit the particular circumstances of a project. Such amendments must be made with care, to avoid introducing ambiguities or inconsistencies with other clauses or other contract documents.

- If the parties make any amendments to the Articles of Agreement or to any other part of the contract, then the alterations should be initialed by both parties.

The Condition

- In the case of most building and engineering projects, there for it is essential that the conditions under which a contract is to be carried out and the obligations, rights and liabilities of the parties should be fully and clearly stated in writing. So when dispute arise it is easy to solve.

- These set out the conditions applicable to the contract and cover all the matters which experience has shown need to be specified in order that both parties may have a clear picture of their rights and obligations.

Bills of Quantity

This provides the best basis for estimating, tender comparisons and contract administration. The contractor’s tenders are therefore judged on price alone as they are all using the same measurement data. This is an efficient approach to the measurement of the works, since only one party is responsible rather than each individual contractor. As a negative, this type of documentation relies on the production of working drawings before tender stage and is time consuming to prepare. It is therefore not a practical approach where time is in short supply. Also, the employer’s acceptance of the risk relating to measurement and design contributes to uncertainty of final cost. Any errors in the Bills must be corrected in accordance with the selected option in the single stage selective tendering document and necessary adjustment to rates and prices must be clearly and neatly made.

Specification

Where the specification is a contract document, all that is necessary is to endorse on the reverse of the last page the words “This is the specification referred to in the contract” with spaces for the signatures as in the case of bills. The schedule of rates should show clearly all corrections and amendments which have been agreed between the surveyor and the contractor.

Condition of Contract

This document sets out the obligations and rights of the parties and the detailed conditions under which a subsequent contract will operate. If a standard form, such as the JCT form, is used it will not be sent out with the invitation to tender. it being assumed that the tenders will have a copy or can readily obtain one. The clause headings will, however, be listed in the first (preliminaries) sections of the bills of quantities and/or specification

Contract Drawings

- It was used in the preparation of the bill of quantity.

- These may either explain and amplify the contract drawing or because of variation identify and explain the changes from the original design

- It is important that the contract drawing precisely define, if they do, should be made the subject of architect’s instructions.

TASK 02

2.1.     Define prime cost sum and provisional sum and explain the reasons for inclusion of these in a building contract.

Prime Cost sums:

The prime cost means, the total cost of the contractor of buying materials, goods and components, of using or hiring plant and of employing labour. In broad sense, the prime cost sums are included in the contract to cover the specialist work or services to be carried out by a nominated sub-contractor and the supply of specific materials or goods to be supplied by a nominated supplier.

The reasons for inclusion of prime cost sums in a contract are:

- In the case of nominated suppliers materials or goods to enable the architect to select articles or materials manufactured by particular firms.

- To cover specialist work and the supply of specific materials, which entail employment of nominated subcontractors or nominated suppliers.

- Function which leaves to maintain the overall objectives and scope of the project as well as to reach the desired quality of project.

Provisional sums:

Provisional sum is a lump sum provided for works or services to be executed by statuary authorities or statuary under takings, or for costs which cannot be precisely determined, defined or undefined at the time the bill of quantities prepared.

The reasons for inclusion of provisional sums in a contract are:

- Their inclusion provides a tender allowance for known work that cannot be properly measured or valued until later in the project.

- Provisional sums are included in the contract bills to cover the cost of work to be executed by statutory authorities who are empowered to carry out their functions by virtue of Acts of Parliament, regulations and byelaws.

2.2. Describe the various matters of details, involved with prime cost sums.

Clause 35 and 36 of the JCT form describe the manner in which way the prime cost sums should dealt with when the contract sum is are adjusted at the end of the contract, the prime cost sums are  deducted and the corresponding actual sums expended are substituted. In practice, various matters of detail are involved, which must be dealt with properly.

These are:

- Discounts

- Net prices and incorrect discounts

- General contractor’s profit

- Attendances on nominated sub-contractors.

Discounts

Discounts are amount by which quoted and stated costs or prices are reduced when paying accounts usually depending on the fulfillment of specified conditions. In practice there are two types of discounts;

- Trade Discounts

- Cash Discounts

Trade Discount

These discounts are customarily allowed of the prices on standard price list of materials and goods in particular trades. This is often done to avoid frequent redaction of such list. This document being varies to allow fluctuation in price. In addition some suppliers will allow larger discount to requited customers or those who buy large quantities.

Cash Discounts

These discount are allow of invoice prices if the contractor pays within certain period in the cost of sub contractor the period is 17 days after issue of the architect certificate which include the value of the invoiced work or services in the cost of suppliers the period is 30 days from the end of the month during which delivery of materials or goods is made.

(It is generally 2.5% in the case of nominated of subcontractors and 5% in the case of nominated suppliers.)

Net price and incorrect cash discount

Sometimes sub contractor and suppliers code net price (that is price exclusive of cash discount) or prices inclusive of cash discount but at the working percentage the provision of the standard form give the contractor the right to the appropriate discount and the employer the right not have to pay more than the appropriate discount.

The use of JCT standard form of nominated sub contractor tender NCC/N ensures that discount include in sub contractor tenders is correct as it refers in part ii to the cash discount allowable to the main contractor under sub contract NSC/C clause 4.16.1.1 that is 2.5% however in cases where the standard procedures is not followed difficult regard to discount may arrives and consideration need to be given the proper way to deal with them.

General Contractors Profit

Prime cost sums are to be exclusive of the general contractors profit provision is made in the BOQ and specification for a separate addition which is normally calculated as a percentage of P.C. Sum the tendered stating the percentage that he requires when the contract sum is adjusted by the omission of P.C. Sum and the substitution of actual costs incurred the profit amount also should be adjusted prorate by applying the same percentage to the actual cost.

Same times the profit additions may be shown as lump sums without any indication of the method of calculation in this case a such sums should be adjusted prorate to the actual cost in the event of the employer paying a sub contractor direct for any reason the general contractor is still entitled to the profit addition as this is a management fees.

Attendance

A general contractor ha to attend upon nominated sub contractor as his responsible for their work and the integration of sub contract work in to the main contract works. Where there are bills of quantities, general attendances are given together in one item and individual items are given for special attendance on each subcontractor as requires. Clause A42 of SMM defined the general attendance and a special attendance is defined under clause A51 of the SMM.

2.3 Adjust prime const and provisional sums

| Ref. No | Description | Omission (Rs) | Addition (Rs) |
| --- | --- | --- | --- |
| 01 02 03 | Prime Cost sums Nominated sub-contractor pilling PC sum in BOQ Add 5 % profit pilling NSC account date 26/06/2008 Add 5 % profit Net Omission carried to summery Asphalt tanking PC sum in BOQ Add 5 % profit Asphalt NSC account date 20/09/2008 Ddt material cost Add 5 % profit Net Omission carried to summery Nominated suppliers Kitchen fitments PC sum in BOQ Add 5 % profit kitchen NS account Deducts 2.5 % discount Add 5 % discount (313,462.50 x 1/19) Net Omission carried to summery | 1,170,000.00 58,500.00 | 1,134,000.00 56,700.00 |
|  |  | 1,228,500.00 (1,190,700.00) | 1,190,700.00 141,070.00 (580.00) 140,490.00 7,024.50 |
|  |  | 37800.00 162,000.00 8,100.00 |  |
|  |  | 170,100.00 (147,514.50) 22,585.50 360,000.00 18,000.00 | 147,514.50 |
|  |  |  | 321,500.00 (8,037.50) |
|  |  |  | 313,462.50 16,498.02 |
|  |  |  | 329,960.52 16,498.02 |
|  |  | 378,000.00 (346,458.54) | 346,458.54 |
|  |  | 31,541.46 |  |

| 04 05 06 07 | ironmongery PC sum in the BOQ Add 5 % profit Ironmongery NS account Add 5 % profit Net Addition carried to summery Provisional Sums Statutory bodies. Water main connection P. Sum in BOQ Payment to water board Add 5 % profit Net Addition carried to summery Electrical main Connection P. Sum in BOQ Payment made to EB Add 5 % profit Net Addition carried to summery Gas main Connection P. Sum in BOQ Payment made to Gas company Add 5 % profit Net Addition carried to summery | 270,000.00 13,500.00 | 292,300.00 13068.00 305,368.00 15,268.40 |
| --- | --- | --- | --- |
|  |  | 283,500.00 | 320,636.40 (283,500.00) |
|  |  | 66,000.00 | 37,136.40 65,456.00 3,272.80 |
|  |  | 66,000.00 56,000.00 | 68,728.80 (66,000.00) |
|  |  |  | 2,728.80 56,343.00 2,817.15 |
|  |  | 56000.00 44,000.00 | 59,160.15 (56000.00) |
|  |  |  | 3,160.15 42,419.00 2,120.95 |
|  |  | 44,000.00 | 44,539.95 (44,000.00) |
|  |  |  | 539.95 |

| 08 09 10 11 | Sewer main Connection P. Sum in BOQ Payment made Add 5 % profit Net Addition carried to summery - Other works. Day work P. Sum in BOQ No work under Day work Net Omission carried to summery Telephone call P. Sum in BOQ Telephone bill was Add 5 % profit Net Omission carried to summery Security Installation P. Sum in BOQ Payment made to security company Add 5 % profit Net Addition to summery | 70,000.00 | 67,982.00 3,399.10 |
| --- | --- | --- | --- |
|  |  | 70,000.00 60,000.00 | 71,381.10 70,000.00 |
|  |  |  | 1,381.10 00000.00 |
|  |  | 60,000.00 00000.00 | 00000.00 8,643.50 432.17 |
|  |  | 60,000.00 9,500.00 |  |
|  |  | 9,500.00 9,075.67 | 9,075.67 61,250.00 3,062.50 |
|  |  | 424.33 60,000.00 |  |
|  |  | 60,000.00 | 64,312.50 60,000.00 |
|  |  |  | 4,312.50 |

| 12 | Contingencies P. Sum in BOQ Was not used Net Omission carried to summery | 75,000.00 | 00,000.00 |
| --- | --- | --- | --- |
|  |  | 75,000.00 0000.00 75,000.00 |  |

Prime Cost and Provisional Sum Summery

| Description | Omission | Addition |
| --- | --- | --- |
| Prime Cost - pilling - asphalt tanking - kitchen fitments - ironmongery Provisional Sum - Water main connection - Electrical main connection - Gas main connection - Sewer main connection - Day works - Telephone call - Security installation - Contingencies Total Omission. | 37,800.00 22,585.50 31,541.46 60,000.00 424.33 75,000.00 | 37,136.40 2,728.80 3,160.15 539.95 1,381.10 4,312.50 |
|  | 227,351.29 (49,258.90) 178,092.39 | 49,258.90 |

### Task 03

### 3.1. Analyze the situation in which variations might arise in a construction project (use the definition for variations as stipulated in JCT standard form of building contract).

Variation

The term variation is clearly defined in the Clause 13.1 of the JCT standard form. It is define variation is the alteration or modification on the design, quality or quantity of the work including the addition, omission or substitution of any work or the alteration of the kind or standard of any of the materials or goods to be used in the work.

Variations may arise in any of the following situations. (According to the JCT form)

- When the architect needs or wishes to vary the design or the specification.

- When a discrepancy is discovered between any two or more of the contract documents (clause 2.3).

- When a discrepancy is discovered between any statutory requirement and any of the contract documents (clause 6.1).

- When an error in or omission from the contract bills is discovered (clause 2.2).

- When the description of a provisional sum for defined work in the contract bills does not provide the information required by General Rule 10.3 of SMM7 (clause 2.2).

The largest number of variations arises under (1) above. In cases 1, 2 and 3, the architect is required to issue instructions but it isn’t needed for cases 4 & 5. All such instructions must be in writing. Although the architect can order any variation that he wishes, the contractor is bound to carry out such an order only if it is in the form of a written instruction issued by the architect.

The contractor is safeguarded, however, in the event of instructions being given orally. Under clause 4.3 of the JCT Form, an oral instruction ‘shall be confirmed in writing by the contractor to the architect within seven days’. The architect has the opportunity during seven days following receipt of that confirmation to dissent; otherwise the instruction becomes effective immediately. Failing such action, the architect may issue a confirmation at any later time but prior to the issue of the Final Certificate.

  - Identify and describe the appropriate ways of valuing the valuations.

There are several ways of valuing variations, the choice in a particular case being that which is appropriate to the circumstances. They are described below:

- By the inclusion in the variation accounts of a lump sum in accordance with a quotation submitted by the contractor and accepted by the architect.

- By pricing measured items in the variations accounts.

- By ascertaining the total prime cost of additional work and applying appropriate percentage additions.

In JCT forms Clause 13.4.1.1 lays the duty of valuing variations upon the consultant’s quantity surveyor who has the right to decide the appropriate method and means of valuing them in each situation

Contractor’s accepted quotation:

Where the architect provides adequate information in an AI, clause 13A of the JCT Form makes provision for the contractor, to submit to the surveyor a quotation for carrying out the specified work.

The works might include the works to be carried out by nominated subcontractors from whom the contractor may obtain quotations for inclusion in his 13A quotation.

The 13A quotation to show separately and in sufficient detail the value of the adjustment to the contract sum, including the effect on any other work with supporting calculations based on rates and prices in the contract bills; any adjustment of time required for completion of the works; the amount to be paid in lieu of the value of loss and or expense under clause 26.1; and a fair and reasonable sum for preparing the 13A quotation.

If the contractor does not agree to provide a 13A quotation the variation will be valued in the normal way under the valuation rules in clause 13.5. If the employer has not accepted the 13A quotation by the end of the seven days allowed for acceptance, the architect may instruct the contractor either that the variation to be carried out and valued under the variation rules in clause 13.5 or that it is not to be carried out. In either case a fair and reasonable amount is to be paid to the contractor to preparing the 13A quotation.

Pricing measured items:

Clause 13 of the JCT form explicit about the way the measured items should be priced. The prices in the bills or schedule of rates are to be used. This is subject to the proviso that the character of the work and the conditions of its execution are similar to that in the project as originally envisage. This covers omission and much of the additions.

Some items will bear no relationship or comparison at all with items in the contract bills, or may not be carried out under similar conditions to similar items in the bills. In these cases a fair valuation is to be done. This mean that a unit rate have to be built up from the prime cost of the necessary materials and using labour constants valued at all in labour rates and with any appropriate allowances for plant and with additions for overheads and profit.

In between the two foregoing groups of item, there is a third group in which the items are not exactly the same as but bear a fairly close resemblance to items in the bills or schedule of rats. They should be priced on the basis of the price of the comparable items. That means in effect, that the pricing of such item is to be done at the same level of prices as it contained in the contract documents.

Prime cost plus percentage additions:

This method of valuing variations is commonly known as daywork and bears a close resemblance to the valuation of work under the prime cost or cost reimbursement type of contract. Day work is a method of payment by the reimbursement to the contractor of the prime cost of all materials, labour and plant used in the carrying out of the work, with a percentage addition to the total cost of each of those groups for overheads and profit.

The contractor is required to submit ‘vouchers’ known as daywork sheets, not later than the end of the week following that in which the daywork was completed, giving full details of labour, materials and plant used in carrying it out. These vouchers should be verified by the architect or his authorized representative. If there is a clerk of works, he can usually be relied upon to do the verifying. The surveyor may be prepared to accept unverified daywork sheets where he is able to satisfy himself that the claim is reasonable, but to do so is not strictly within the terms of the Standard Forms. The signature denoting verification by the architect or his representative relates only to the material used and time spent and not to the correctness or otherwise of any prices included.

The rates and prices used for valuing daywork should be those current at the time the work was carried out, not those current at the date of tender. The method of computing standard hourly based rates for use in pricing dayworks illustrated in the Definition of Prime Cost of Dayworks.

Task 3.3

Task 04

4.1 Describe the methods of adjusting the contract sum in respect of formula method of ascertaining the fluctuations

Definition

Any contract, other than a prime cost contract, will be either ‘firm price’ or ‘fluctuating price’. Firm price contracts are those where reimbursement of changes in costs is limited to those relating to statutory contributions, levies and taxes. Fluctuating price contracts are those containing provisions for reimbursement of changes in a wide range of labour costs and materials prices in addition to statutory costs. It should be recognized that the term ‘fluctuations’ includes both increases and decreases and that they may lead to payments becoming due to the contractor from the Employer and vice versa.

The JCT form contains three different provisions, any one of which may be incorporated in a contract by deleting the other two clauses in the appendix to the condition to the Contract Particulars. These provisions are,

- Adjustment of contract sum limited to fluctuation in statuary contribution taxes and levies and as specified clause 38

- The adjustment of contract sum in respect of labour and material cost and in statutory contributions levies and taxes as specified in clause 39.

- Adjustment of contract sum in respect of fluctuation as in “b” above by the use of price adjustment formula as specified in  clause 40

Clause 38 & Clause 39 above relate to the traditional method of reimbursement of the actual amounts of fluctuation allowed under the respective clauses of the contract and C to the formula method of calculating by use of formula a sum to compensate for lost due to fluctuation.

There are two method were used to the fluctuation, theses are

- Traditional method

- Fluctuation method

Traditional method

The object of the traditional method is to ascertain the actual amount of the fluctuation in costs and price within the scope of the appropriate clauses of the contract as stated above. These amounts are very less, sometime than the actual costs and price have really fluctuated, due to the limitation imposed by the operation of the contract clauses.

Formula fluctuations

The object of the formula method of reimbursement is to calculate a sum which will compensate the parties to the contract for loss incurred due to increase and decrease of the costs. No attend is made to calculate the actual amount of loss involved.

The JCT form refers in clause 40.1 to separate documents called the Formula Rules which sets out the formula and defines their use. By virtue of the provisions of clause 40, the Formula Rules are made part of the Standard form and therefore, contractually binding on the parties.

The formulae is by means of indices, published monthly by the Department of Environment, which measure the fluctuations in costs of building work classified in 60 categories. The indices are indented to be applied monthly to the sums included in interim valuations, thus ensuring that the payment of fluctuation is made promptly. the index numbers for each category is based upon price movements of a number of selected items of labour,material and plant which are calculated from a range of contracts.

Preparatory work necessary before using the formulae

The formula Rules give a formula  for application to each work category (Rule 9 (,a second one relative to balance of adjustable work ( I .e  work ranging for adjustments, but which is not capable of allocation to any work category ) ( Rule 26 ) and third formula for use for valuations after practical completion and the Final certificate(Rule 28 ) After giving corresponding formulae for use with work groups ( Rules 29 & 38 ), five formulae applicable to five types of specialist engineering installations are given ( Rules 50,54,58,63 & 69 )

In order to apply the appropriate formula to each work category, all the measured work items in the Bells of quantities must be allocated to work categories. This should be done before tenders are invited either by annotating the Bills or by preparing schedules.

There will be some work or goods the value of which is included in a valuation which cannot easily be allocated to work categories o0r which is excluded from adjustments and this is deal with as discussed below.

Balance of adjustable work

This is the balance of main contractor work which ranks for adjustment but which is not allocated to work categories or to which and engineering formula does not apply

Eg : Preliminarys

Water for the work

Insurance

Attendances on nominated sub – contractors

Provisional sums

Provisional sums for work which will be paid at the current rate are not allocated to work categories but are separately identified as not subject to adjustments.

Fixing of items supplied by the clients or nominated suppliers fixing only items may be deal with either4 by:

- Allocating to an appropriate work category

- Including in the balance of adjustable work

- Appling an index specially created for the purpose

Variations

All items priced at Bill rate analogous rates or at rates currents at the base date will rank for adjustments and should be allocated to work categories. Variations valued on a daywork basis or otherwise valued at rates or prices current at the date of execution should be excluded from the operation of the formula.

Payments to nominated sub contractors and suppliers

Such payments including profit are excluded from the adjustment.

Unfixed material and goods

The value of unfixed materials and goods is also included from adjustments.

Claims for loss or expense

Claims for extra payments under clauses 26 & 34.3 are excluded from the adjustment.

Calculated adjustment amount

The appropriate formula is applied to each part of the value of work included in a valuation when it has been appropriate into:

A ) work category

B) Balance of adjustment work

c) In specialist engineering installation

Such applications are subject to the following considerations

Provisional indices

Base month

Valuation period

Non adjustable elements

Retention

The fluctuation amounts calculated by the formula method , unlike those ascertain by the traditional method, are subject to retention deduction.

TASK 5

5.1 explain the contractor's claims in a building contract

Claims

Claim means a written demand or written assertion by one of the contracting parties seeking, as a matter of right, the payment of money in a sum certain, the adjustment or explanation of contract terms, or other relief arising under or relating to the contract.

In the construction process; there are three contractors’ claims available. These are;

- Common law claims

- Ex gratia claims

- Contractual claims

Common law claims

These arise from causes which are outside the express terms of the contract. These claims arisen if the employer or his agents breaches any terms of the contract.

Ex: If the employer in some way hindered progress of the works or if the architect were negligent in carrying out his duties, resulting in loss to the contractor.

Ex gratia claims

These have no legal basis but are claims which the contractor considers the employer has a moral duty to meet. The employer is under no obligation to meet such ‘hardship claims’ but may prepare to do so grounds of natural justice or to help the contractor where otherwise he might be forced into liquidation.

Ex: If he has seriously under priced an item whose quantity has been increased substantially because of a variation or the re measurements of a provisional item, which will in consequence, cause him considerable loss.

Contractual claims

Contractual claims are those which arise from specific Clause in the General Conditions of a Conditions of Contract, which provide for a contractor to make a claim. This is a most important fact and frequently not properly understood by contractors when submitting their claims to the employer. From the very outset it must be understood that initial acceptance of a claim lies in the contractor’s ability to determine with precision under which Clause of the General Conditions of Contract the claim is to be made.

These arise from express term of the contract and form by far the most common kind of claims. They may relate to any or all of the following.

- Fluctuation

- Variation

- Extension of time

- Loss and/or expense due to matters affecting regular progress of the work

Fluctuation Claims

These relate to increase in the cost labour, material and plant and to levies, contributions and taxes which the contract provides for the contractor to be reimbursed by the traditional method in clause 38 and 39 of the JCT form.

Claims Arising From Variations

These may relate to one or more of the following;

- Clause 13.5.1.2 of the JCT form provide the quantity surveyor to value the variations using the bill rate which are similar corrector and under similar conditions.

- Clause 13.5.3.3 of the JCT form provides the contractor to claim the adjustment of one or more preliminary items which has not been adjusted by the PQS in the valuation of variations.

- Clause 13.5.5 states that inconsequence of a variation the condition under which other work is carried out has change and therefore the bill rate for that work should be adjusted to reflect the change conditions.

- Clause 13.5.6 states that any of the bases of claim described above three points will also apply to performance specified work to which this is clause relate.

- Clause 13.5.7 provides the contractor to claim additional cost incurred due to a variation order but for which he has not been reimbursed by the application of the normal valuation rules.

5.2 describe the headings of a claim in order to prepare a clear and orderly presentation of the data

Heads of the clime may be any or all of the following

- In sufficient use of labour or plant

- Increase in cost of labour materials etc. during the period of distribution

- Site running cost

- Head office overhead

- Finance charges and interest

- Loss of profit

In sufficient use of labour or plant

This refers to men and plant standing idle or working at a reduce level of out put. It would be necessary for the contractor in substantiating a clime to produce evidence of the estimated levels of output used in preparing his tender and records of the actual out put during the disruption period.

Increase in cost of labour materials etc. during the period of distribution

Increases in cost would normally only apply in the case of firm price contracts, although they could possible apply in the case of fluctuations contracts using clauses 38 or 39, in respect of materials, etc. not listed on the list of  basic prices of materials.

Site running cost

Relate to site staff costs, offices, mess-rooms, sheds, rates on temporary buildings etc. normally referred to as preliminaries of a contract could result in or some or all of these items being required for a period excess of that for which the contractor allow in his tender.

Head office overhead

This includes cost of maintaining head and branch offices, plants and materials yard rents, rates, directors, & staff salaries, office running expenses, professional fees and depreciation.

Finance charges and interest

These are interest chargers incurred by the contractor on money he has had to barrow in order to finance direct loss and/ or expense claimed. The rate of such interested must be those actually paid to the bank or other finance source and certified by the contractor’s auditors. Interest due to late payment of sums owning is not admissible.

Loss of profit

This refers to profit which the contractor could behave earned but was prevented from earning as a direct result of one or more  of the matters listed in clauses 26.2 this could arise where the architect omitted substantial pert of the project. In such a case, the contractor would be entitled to reimbursement of the profit which he could prove he would made had he been allow to complete the contract as originally an envisaged.

It should be noted that acceleration costs, i.e. additional costs incurred due to speeding up progress of a contract in order to meet the completion date, are not recoverable, nor are ascertained.

TASK 06

6.1. Describe the methods of payment for permanent works and preliminaries.

- Payment methods for permanent works

Permanent Works means the permanent works to be executed by the Contractor under the Contract. The following payment methods are the common methods in general those are:

- Stage payments

- Interim payments

Stage payments

Stage payments as an alternative to regular monthly certificates contract conditions might provide for stage payments that are for payment to be made when certain defined stages in the construction work have been completed this method of payment normally used for based on drawing and specification contract.

Interim payments

The amount of any constant payment is calculated by determining the total value of work executed, plus the value of materials on site (only if this is allowed under the contract) and any other amount specified as being payable under the contract. All previous payments are then deducted and the difference is the amount due. Nevertheless, the total amount of payments made under this procedure should not exceed the contract price.

Payment method for the Preliminaries

The preliminary or general conditions section of the BOQ provides the high-level overview of the project, particulars, the project and the parties to the contract including a description of the project and the site and details of the conditions of contract to be used, but the preliminaries will also include a considerable amount of more detailed information about specific issues. It can readily be seen that, although the preliminaries section typically contains a very large amount of written information, only some of the items are actually price able. Information covered in the preliminaries section can therefore be divided such as

- General project details

- Contractual matters

- Specific requirements of the employer

- Contractor’s general cost items

- Information about works to be executed by persons other then the main contractor or which may be subject to later instructions.

For the purposes of interim valuation, preliminaries evaluation will depend on the level of detail in the pricing of the original document and what the contractor’s estimator has included in their assessment. Some contractors will include preliminaries as lum sum which makes accurate assessment impossible: some will include all the project profit, whereas others will spread either all or part of their profit throughout the measured section of the bill of quantities.

There is no reason why preliminaries cannot be included within a schedule of stage payments: however, more accurate assessment is preferable, as explained below. It is there for customary to treat the valuation of preliminaries separately at the outset of each interim valuation. Individual items are claimed as a percentage of their total value or, as is more generally the case, the preliminaries are subdivided into their “fixed” or “time related” sections and the amounts apportioned to each interim valuation.

This method allows point load items, such as site establishment costs and scaffolding to be fully included within the interim valuation, relative to when they are expended it allows for the retention of monies for the site clearance and final cleaning, and facilities the time related items to be spread over the whole of the contract period. The methodology satisfies the needs of both quantity surveyors.

Preliminaries items are of four kinds, such as:

- Cost-Related Items

- Time-Related Items

- Single-Payment Items

- A combination of Two or More of the Others

6.2. Discuss the items to be included in an interim valuation.

Preliminaries:

This section of BOQ should be broken down into separate amount to be included in the interim valuation. This process will be easier and result more satisfactory if there is a contract sum analysis which source he total of preliminaries included in the tender. The contractor will be able to produced the billed up of the tender sum and the individual amounts allowed in it for the main preliminaries items. These amounts will be available for valuation purposes the adjustment of preliminaries in the final account if necessary.

Main contractor’s work:

The value of the work carried out by the contractor’s own workforce will be readily ascertainable from the measured work sections of the bills of quantities. The prices contained in the bills of quantities will be used in the valuation of the main contractor’s work, regardless of whether the contractor underpriced or overpriced the work when compiling the tender.

The surveyor, when valuing the main contractor’s work, will begin with the groundwork section and proceed in order through all the succeeding work sections which contain items of work which have been wholly or partly carried out.

Variations:

Very few projects, if any, have no variations. On some jobs they number in double or even treble figures. They present a difficulty in the context of interim valuations for several reasons. Clause 30.2.1.1 of the JCT Form requires that effect be given in Interim Certificates to the measurement and valuation of variations. For this to be done each variation should be valued either approximately or accurately, as soon as possible after issue. The question of how best to deal with the effect of omissions in the measured sections of the bills of quantities is bound to arise.

There are two alternatives:

- The first is to ignore variations when dealing with the work measured in the bills and the omission to be allowed for when adding the net value of variations.

- To take the omissions into account when valuing main contractor’s work and adding the value of additions only against the variations subhead.

In practice, a combination of these two alternatives will serve best. The first may be used as a general rule and the second being used where a complete section or group of items in the bills is affected by a variation.

Unfixed materials and goods:

Unfixed materials and goods are categorized under two separate headings. There are:

Materials on site

Clause 30.2.1.2 of the JCT Form requires the inclusion in the amount of an interim certificate of materials and goods delivered to the site for incorporation in the Works. In order to value them, the surveyor will need to be satisfied that the materials and goods are actually on the site and to ascertain approximately how much of each material or good there is. It is not necessary to know the exact quantities because by the time the next valuation is done, most or all of the materials will have been incorporated into finished work which will then be valued as such.

It will be necessary to reduce or exclude the invoice value of:

- Insufficiently protected materials or those which have deteriorated or been damaged;

- Quantities which are clearly in excess of requirements; and

- Any materials or goods which have been delivered prematurely, that is, when the length of time before they are likely to be required is unreasonably long.

- Materials which are in not in accordance with the specification given.

Materials off site

The JCT Form includes a provision in clauses 30.3; the value of materials and goods intended for the Works but not yet delivered to the site to be included in the certificate amount at the discretion of the architect, subject to the following extra conditions. They are:

- That they are intended for incorporation into the works and are in accordance with the contract and that they need only be transported to the site to be ready for use.

- That they are set at the place where they are being kept and are clearly identifiable and appropriately marked.

- The ownership is established in written contract or subcontracts for their supply.

- That they are properly and adequately insured.

Statutory fees and charges:

Any sums paid by the contractor to any local authority or statutory undertaker in respect of fees or charges for work executed or materials or goods supplied in the course of carrying out its statutory obligations should be included in the next interim valuation.

Nominated subcontractor work:

Clause 4.17 of the JCT Nominated Subcontract Conditions states in detail what should be included in respect of subcontract works. The nominated sub contractors should make applications from time to time, through the main contractor, for the amounts on accounts to which they consider they are entitle.  Clause 35.13.3 of the JCT form requires the contractor to provide proof of payment to any nominated subcontractor of any sum included in the immediately preceding certificates in respect of their work, materials or good. Should such proof not be forthcoming in respect of any sum the quantity surveyor should inform the architect accordingly, so that he may proceed in the manner prescribed in clause 35.13.5 of the JCT Form.

Nominated suppliers good:

The value of goods or materials supplied by the nominated suppliers should be included in the valuations on the same basis as those supplied by non-nominated suppliers as previously described.

Fluctuations in costs of materials and goods:

The amounts, if any, under this heading which should be included in interim valuations, will vary according to whether the contract is a firm price or fluctuating price one. There are two points to be remembered

- Where the traditional method of recovery is allowed for in the contract conditions, amounts due should be included in interim valuations as early as possible

- The amounts of fluctuations calculated by that method are payable in full with the percentage addition stated in the appendix referred to in clause 39.8 of the JCT Form.

Retention

There is a provision in all standard forms of building contract for a percentage of the valuation total to be deducted. This money is to be retained by the employer and it is called retention in the JCT form. The purpose of retaining part of the total value of the work completed to date is

- To reduce the employer to some extent against the affect of the contractor defaulting.

- To provide as intensive for the contractor to complete the work properly.

6.3(a). Prepare a breakdown the preliminaries section to be included in interim Valuations, using the data sheets given.

| Ref No. | Description | Initial Cost % | Running Cost % | Final Cost % |
| --- | --- | --- | --- | --- |
| 23. 24. | Construction Management Service Plant & Equipment Office for employer Sanitary Accommodation for employer Contractors Site Accommodation Water for the Work Electricity for the work Maintenance of public roads etc. Protection of public & Private services Protection of waterways Temporary roads Temporary hoardings & Gantries Name board Samples & testing Final cleaning Provision of security bonds & Guarantees Provision of performance bond All risk insurance Insurance against injury Provision for progress charts etc. Payments to local authorities etc. Setting out the works Site security lighting etc. Safety, health and welfare | 00 60 60 60 70 30 30 00 00 00 70 70 90 00 00 100 100 00 00 00 100 100 30 30 | 100 30 30 30 24 60 60 100 100 100 24 24 00 100 00 00 00 100 100 100 00 00 60 60 | 00 10 10 10 6 10 10 00 00 00 6 6 10 00 100 00 00 00 00 00 00 00 10 10 |

6.3(b). Prepare the interim Valuation No.7, Statement of retention and nominated subcontractors Values by using the attached abstract sheets.

Valuation No: - 07		Valuation Date: - 27 / 02 / 2008                   he JCT Form.gress of a contract in order to meet the completion date, are not recoverable, nor are ascertain

| Preliminaries 666,533.34 Substructure 100 % completed Superstructure & finishes Concrete work 100 % completed Masonry work 100 % completed Water proofing 100 % completed Woodwork 100 % completed Roof covering and plumbing 100 % completed Plumb & sanitary install. 80 % of 1850,000.00 Floor wall & ceiling 40 % of 2,345,000.00 External work Drainage 90 % of 825,000.00 Fencing 75 % of 750,000.00 Nominated sub contractor Metal work 30 % of 850,000.00 Special attendance Profit 5 % of 255,000.000500.00255,000.00/850,00 Material at site Electrical installation 60 % of 775,000.0055,000.00 Special attendance Profit 5 % of 465,000.00 Material at site Nominated suppliers goods Sanitary fittings Profit 5 % of 465,320.00 | 666,533.34 2,125,000.00 TEC HND in Quantity Surveyingent full .ms.oper execution of the contract. modifications. f different contracts, major and subsi 4,675,0004.00 1,423,000.00 122,500.00 1,450,000.00 2,700,000.00 1,480,000.00 938,000.00 742,500.00 562,500.00 255,000.00 22,500.00 12,750.00 400,000.00 465,000.00 39,000.00 23,250.00 50,000.00 465,320.00 23,266.00 | 666,533.34 2,125,000.00 12,788,500.00 |
| --- | --- | --- |
|  |  | 15,581,033.34 1,305,000.00 |
|  |  | 16,886,033.34 690,250.00 |
|  |  | 17,576,283.34 577,250.00 |
|  |  | 18,153,533.34 488,586.00 |
|  |  | 18,642,119.34 |

| Money provisions Electrical main connection Water main connection Variations Fluctuation Claims Material at site Cement 60 bags @ Rs. 600.00 Sand 10 m3 @ Rs. 1800.00 Lime 3 tones @ Rs. 6000.00 Total value of work done Amount subject to NIL retention. Money provisions Fluctuation Claims Amount subject to Retention | 83,250.00 68,730.00 300,406.00 173,000.00 42,000.00 36,000.00 18,000.00 18,000.00 151,980.00 173,000.00 42,000.00 | 18,642,119.34 151,980.00 |
| --- | --- | --- |
|  |  | 18,794,099.34 515,406.00 |
|  |  | 19,309,505.34 72,000.00 |
|  |  | 19,381,505.34 |
|  | 366,980.00 19,381,505.34 (366,980.00) |  |
|  | 19,014,525.34 |  |

| Retention 5 % of 19,014,525.34 Recovery of advance 20 % of 17,625,419.34 Ddt. previous payments Balance Due | 950,726,27 3,525,083.87 13,400,000.00 | 19,381,505.34 (4,475,810.14) |
| --- | --- | --- |
|  |  | 14,905,695.20 (13,400,000.00) |
|  |  | 1,505,695.20 |

Task 6.4 Preparation of Final Account for this Project

Valuation No: - 12		Valuation Date: - 26 / 09 / 2009

| Preliminaries Substructure 100 % completed Superstructure 100 % completed External work 100 % completed Nominated sub contractor Metal work Special attendance Profit 5 % of 888,758.00 Electrical installation Special attendance Profit 5 % of 763,860.00 Nominated suppliers goods Sanitary fittings Profit 5 % of 465,320.00 Money provisions Electrical main connection Water main connection Variations Fluctuation Claims Total value of work done | 1,000,000.00 2,125,000.00 15,580,500.00 1,575,000.00 888,758.00 75,000.008.00.00uation Date: - 27 44,437.90 763,860.00 65,000.00 38,193.00 465,320.00 23,266.00 83,250.00 68,730.00 300,406.00 372,170.00 152,980.00 | 1,000,000.00 19,280,500.00 1,008,195.90 867,053.00 488,586.00 151,980.00 825,556.00 |
| --- | --- | --- |
|  |  | 23,621,870.90 |

| Amount subject to NIL retention. Ddt Money provisions Fluctuation Claims Amount subject to Retention Retention 5 % of 22,944,740.90 Recovery of advance 20 % Previous payments Add Retention released 50 % of 1,147,237.05 Balance Due | 151,980.00 372,170.00 152,980.00 | 23,621,870.90 (5,203,337.05) |
| --- | --- | --- |
|  | 677,130.00 23,621,870.90 (677,130.00) |  |
|  | 22,944,740.90 1,147,237.05 4,056,100.00 17,659,000.00 573,618.53 |  |
|  |  | 18,418,533.85 (17,659,000.00) |
|  |  | 759,533.85 573,618.53 |
|  |  | 1,333,152.38 |

FINAL ACCOUNT STATEMENT

| Contract Sum Deduction Nominated sub contract work Nominated suppliers work Money provisions Contingencies Additions Nominated sub contract work Nominated suppliers work Money provisions Variations Fluctuations Claims Deduct net contract payment Advance payment Previous payments Balance due | Omission 1,846,250.00 525,000.00 150,000.00 400,000.00 2,921,250.00 4,056,100.00 18,991,065.36 | Addition 23,201,750.00 1,875,248.90 488,586.00 151,980.00 300,406.00 372,170.00 152,980.00 26,543,120.90 (2,921,250.00) 23,621,870.90 (23,047,165.36) 574,705.54 |
| --- | --- | --- |

TASK 7

7.1. (A) Illustrate the potential causes for disputes during constructions.

Several types of disputes may commonly occur in the constructions contracts. Many of them are resolved at the earlier stage. Some of them may lead up to the breach of contract. Relationship within constructions between clients, contractors and other parties are often adversarial. The process of construction contract is complex and obligation is often very difficult.  Therefore the risks associated with constructions project can be high. Since the demand is put on the construction industry through competitive bidding procedure.  The adversity of project can obviously increase. Those issues may increase the possibilities for disputes.

The disputes comes during the construction when the followings incidences occur,

- Variation

- Fluctuation

- Retention

- Liquidated damages

- Working quality

Contingency Sum

This is a sum included in a contract to cover the cost of work or expense not contemplated or implied in the contract sum. This money is to be expended at the discretion of the architect, and where no unforeseen circumstances arise this figure constitutes a saving to the employer. This provides an opportunity for the employer to secure the execution of essential additional work within the contract sum. For example, underground structures and services may be discovered which were not previously known to exist. Work must be carried out on them before the contract works can be continued and the extra cost of this work must be met by the employer.

Adverse physical conditions

The following physical conditions may warrant a claim for additional payment provided, of course, they were unknown at the time tender:

- Wells

- waterways

- geological faults

- ground conditions different from those anticipated

- subsidence

- unpredictable water tables

An unforeseen physical condition may be stated to have been encountered if the ground conditions are materially harder than those anticipated, on the hand, and if they are substantially softer than anticipated, on the other.

- Differentiate Adversarial and Non- Adversarial methods in dispute resolution.

Adversarial dispute resolution system.

Where a dispute arises under a construction contract, the first means of resolving that dispute in a binding manner is often through a decision of the contract administrator. Through this method disputes will be resolved with actions of court. Give below are some of the Adversarial dispute resolution systems.

Arbitration

This is the formal settlement of a dispute by a third person chosen by the disputing parties. It is an alternative method to court action. But, it is impossible to avoid recourse to the courts by agreement, as any such agreement or contractual clause to that effect is void at common law for being contrary to public policy.

Litigation.

Disputes can be resolved directly by the parties involve in the disputes either dealt with by the court or referred to arbitration. Litigation involves one party issuing a writ against another. The parties are required to prepare a case in support of their argument and this is heard in the court. The mechanics of litigation are governed by statute. Decisions are maid on the basis of the evidence presented together with the application of relevant registration and precedent. The process is long and expensive and can be damaging the business relationship. The role of the quantity surveyor in litigation will be as a witness of fact or as an expert witness. Expert witness will be called by a party to a dispute to give expert evidence of opinion to support an argument.

Non adversarial dispute resolution system.

Non adversarial dispute resolution systems are the systems where the disputes are resolved with out any action of court. These systems are called as alternative dispute resolution systems. Give below are some of the Non adversarial dispute resolution system.

Adjudication

Adjudication is a process aimed at providing a quick, non-binding solution to a dispute. The process involves an agreed third party giving a decision on disputes relating to a contract as and when they are referred to that third party. The adjudicator, together with the procedures and the types of dispute which can be referred to adjudication, will all be agreed and stated in the conditions of contract. For adjudication to be effective, any decision of the adjudicator must be immediately implemented. Appeal should only be permitted after Practical Completion has been achieved.

Mediation

Both sides are brought together, often in neutral surroundings, and encouraged by a trained mediator to settle their dispute amicably.

A mediator is appointed jointly by the parties, and will normally meet with the together and separately in an attempt to resolve the differences. It is a non adversarial process which tends to forge good relationships between parties.

Mini-trial

A tribunal, usually comprising senior management from the various parties and chaired by an independent adviser, hears presentations made by all parties to the dispute, who may be represented by lawyers. Witnesses and experts may be called to give evidence. Following the presentations, the senior management enters into negotiations, with the objective of reaching an agreed settlement. The chair's role is to facilitate negotiations, adding suggestions and advice as appropriate to encourage agreement. Should settlement not be reached, the chair may, depending upon the agreed procedure, offer a non-binding opinion.

Conciliation

Conciliation is somewhat similar process to mediation. But the conciliator will actively participate in the discussions between the parties offering views on the cases put forward.

Task 7.2 (a) discuss the advantage of using alternative dispute resolution

Alternative dispute resolution is the term used to describe a number of formal, non-adversarial methods of resolving disputes without resorting to the courts or arbitration. The approach was developed in the United States and was introduced to the UK in the 1980s. The processes offer an inexpensive, expeditious and probably more palatable alternative to litigation and arbitration.

As with arbitration and litigation, the processes involve a third party. However, unlike arbitration and litigation, the role of the third party is not to sit in judgement, but to act as a neutral facilitator to a negotiated settlement between the parties.

The advantages of alternative dispute resolution are often referred to as the four Cs. These are:

1. Consensus – This approach requires the agreement of all parties to a resolution of the dispute.    The emphasis is on finding a business, rather than a legal or adversarial, solution to the dispute.

2. Continuity of business relations – the processes is concerned with resolving disputes within the context of, and without permanently damaging, ongoing business relations.

3. Control – resolution of the dispute remains in the control of the parties to it. The parties can concentrate on forging a settlement, which focuses on commercial issues rather than the letter of the law and may thus be less damaging for all parties. Once a dispute is referred to the courts or to arbitration, the parties effectively lose control of the process.

4. Confidentiality – the proceedings are not published, and therefore the damage resulting from adverse publicity is avoided.

One of the requirements of alternative dispute resolution is that it must be non-binding. If the process is not working, recourse to litigation or arbitration, as appropriate, must be available. If agreement is not reached, the process will seldom have been a waste of time, effort and expense. It will probably have clarified or narrowed the scope of a dispute and will undoubtedly reduce some of the information gathering and synthesis requirements of arbitration or litigation. Where an agreement is reached using one of the alternative methods of dispute resolution, it should be formalized into a written agreement between the parties.

b) Evaluate two common methods of Alternative Dispute Resolution.

Alternative dispute resolution (ADR)

Alternative dispute resolutions include a number of formal, non adversarial dispute   resolution methods without resorting to the courts. If any third parties involved who should be neutral. ADR is an inexpensive, quicker and probably more palatable alternative to litigation. If the ADR process is unsuccessful, both parties can recourse the litigation. Some of ADR methods are describe bellow.

Adjudication

Adjudication is a quick and relatively inexpensive way of resolving disputes and may arise in one of three ways. There may be a clause in the contract under which the parties agree that disputes will be referred to adjudication. For example the standard subcontract conditions used on building contracts before the passing of the Housing Grants Construction and Regeneration Act 1996 ( The Construction Act) included an adjudication clause which provided for the referral to adjudication of disputes relating to set off. In the absence of a clause in the contract on projects not covered by The Construction Act, once a dispute has arisen the parties may agree to refer the dispute to adjudication. The third and most widely used adjudication process arises out of The Construction Act. Under this statute either party to a construction contract may refer a dispute at any time to adjudication. The adjudicator may be named in the contract or subject to subsequent agreement of the parties or appointed by one of the adjudication nominating bodies named in the contract such as the RICS, RIBA or Cl. Arb. The Act requires the process to be completed in the form of an adjudicator’s decision within 28 days of his or her appointment. The adjudicator may secure an extra 14 days with the approval of the referring party or both parties can agree to extend the period.

Despite the short time span during which the adjudication takes place, disputes of a complex nature are being referred to adjudication and result in an enforceable decision being given. The adjudication process is popular with those who use it. Despite it being final and binding only until finally determined by arbitration, litigation or agreement it s unusual for the losing party to take the matter any further than the adjudicator’s decision with very few finishing up being referred to court or arbitration.

Mediation

Mediation is a process whereby using a third party facilitator the parties attempt to reach a settlement of the matters in dispute. The mediator does not normally provide a decision or opinion and therefore there is no decision or award to enforce. There are no hard and fast sets of rules governing the manner in which the mediation is conducted or which governs the powers and duties of the mediator. These matters are catered for in the conditions of contract entered into between the parties or as a result of a subsequent agreement. The Centre for Dispute Resolution (CEDR) has however produced a set of guide rules for the conduct of mediation which are useful in respect of this dispute resolution method as there is little by way of tradition, statute or case law to fall back on. If mediation has any chance of achieving a successful settlement it is essential that the person appointed to act as mediator is experienced. Often it is the skill of the mediator which results in a settlement being achieved as otherwise if left to their own devices the parties would perpetuate the old arguments.

The process is very informal with the main thrust being for the parties to reach a commercial settlement. Little time is spent on presenting and arguing the various issues which have resulted in the dispute arising. It is essential that a decision maker from each of the parties is present at the mediation as the object is to achieve a settlement before the mediation is concluded. The process usually takes a day or sometimes two with the parties and mediator being closeted away from the business environment allowing full attention to be in mind the parties may be less open in what they reveal during the mediation process thus reducing the likelihood of an agreed settlement.

CONCLUSION

This was a great opportunity for me to explore into the professional world. I have gained vast knowledge about the contract Administration. Contract Administration interrelated to construction industry has been dealt in detail in the seven consecutive tasks of this assignment.

We could describe the methods of adjusting the contract sum in respect of fluctuations and we also were able to identify and describe the contractor’s claims in a range of situations. It enabled us to learn about the methods of payment for permanent works and preliminaries and what are the items that to be included in an interim valuation.

It gave us a clear idea on inclusion of prime cost sums and provisional sums in a contract sum and to describe various matters in details, involved with prime cost sums. It gave us the knowledge to prepare a summary by adjusting prime cost and provisional sums to include in interim valuation and final accounts using the given information.

We learned about the potential causes for disputes during constructions and to differentiate adversarial and non-adversarial methods in dispute resolution. Alternative Dispute Resolution was very useful in widening our knowledge in order to be a quantity surveyor in the future.

Reference

- British college of Applied Studies Contract Administration Guides Notes given by the assessor Mr. P.B.G. Wickramasinghe.

- John Murdoch and Will Hughes, Construction Contracts Law and Management, 4t Edition,

- Ivor H.Seely, Quantity Surveying Practices,2nd Edition Published by Palgrave Macmillan,

- Jack Ramus, Simon Birchall, Phil Griffiths (2006) Contract Practice For Surveyors. 4th ed. Oxford: Elsevier Ltd.